| PDG ACTIVITY 2023-2024 Add actions only to those elements that you intend to deliver under. PDG BUDGET = £13800 | TIMESCALE | ACTIVITY LEADER | OUTPUT TARGETS |  | INPUTS |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Number of FSM pupils to be supported | Number of family/community engagement activities |  | Budget Required £ | Budget Spent £ |
| Robust identification of need with regard to disadvantaged pupils, their circumstances, current achievement and progress, together with clear procedures for tracking individuals’ progress. |  |  |  |  |  |  |  |
| Analysis of data to identify needs of disadvantaged pupils, target interventions and monitor impact. | Ongoing | SMT | 14 |  |  | £700.00 |  |
| A systematic approach to intervention, support and providing feedback to individual learners, including those at risk of disengaging from learning and whose attendance is a cause for concern. |  |  |  |  |  |  |  |
| Targeted interventions to support pupils who are disadvantaged – ELSA… | Ongoing | ALNCo BW | 14 |  |  | £5500 |  |
| Making provision of high quality for learners experiencing material disadvantage who have additional learning needs, are educated otherwise than at school or have emotional social and behavioural needs. |  |  |  |  |  |  |  |
| Access to enrichment activities, the removal of any financial barriers to participation and the provision of curricular activities and opportunities through out-of-school hours provision and holiday programmes. |  |  |  |  |  |  |  |
| To ensure that FSM pupils can access all out of school activities and enhancement programmes. Subsidise costs for visits and travel for all pupils, in particular pupils from disadvantaged backgrounds | Ongoing throughout the year | HT Admin | 14 | Based on number and cost of trips |  | £3800 |  |
| The provision of additional tuition, small group tuition and other strategies designed to personalise learning and target support and access to facilities beyond the school day that support homework and independent learning, such as those involving ICT. |  |  |  |  |  |  |  |
| The development of personal support and mentoring to meet pupils’ physical, emotional and social needs, to remove barriers to learning and improve well-being and readiness to learn. |  |  |  |  |  |  |  |
| Wellbeing- To further develop’ Helping Hands’ project in house in preparation for transition. | Summer Term | Year 6 teacher | Children identified in Year 6 who would benefit from further support in transition to the comprehensive school | Staff released to support the pupils in accessing the planned extra transition activities |  | £800 |  |
| Elsa Training. | AutumnTerm Ongoing | LSO(BW) |  | Training for new ELSA |  | £1000 |  |
| Establish Emotional Literacy Support and further develop appropriate resources. | Autumn Term | (BW) |  | Resources required to support the ELSA program within school, and budget given to further develop the working space for ELSA sessions to take place |  | £2000 |  |
| The development of strategies that involve the family and community including those that signpost learning opportunities. |  |  |  |  |  |  |  |
| To support BCBC Early help team in signposting support available for children, parents and families. (e.g. ASD parent group, finance advice etc.) | Throughout the year | HT | Signpost all families to support available from the early help team | All |  | No cost- provide accommodation for meetings. | . |
| The embedding of opportunities within the curriculum and in wider learning for learners’ voice to be fully involved in informing decisions that affect their education |  |  |  |  |  |  |  |